## CRR by Lead (27)
ID | Principle Risk | Division | Speciality | Risk Lead/Exec Lead | Opened | Description | Consequence (initial) | Likelihood (initial) | Rating (initial) | Controls | Gaps in controls | Assurances | Gaps in assurances | Consequence (current) | Likelihood (current) | Rating (current) | Action Plan Summary | Consequence (Target) | Likelihood (Target) | Rating (Target) | Risk Review Date | Board Committee
3480 | PR 3 | Unscheduled Care | Emergency Care | Caroline Landon | 2015-06-11 | A&E Estates Due to the layout / size of A&E department and increase in activity, the A&E dept: 1. lacks space to offload ambulances leading to queues in the corridor; 2. Isolate infectious patients 3. Non compliant with Royal Society of Psychiatrists for a suitable / safe mental health room 4. lack of space for triage (initial assessment for clinicians) 5. May possibly breach single sex accomodation in CDU this has an adverse impact on the quality and saftey of the service, working environment for staff and efficiency / ability to meet key performance targets. | 4 | 5 | 20 | Reduced number of bays in CDU to avoid single sex breaches RGN sits in with reception staff when patients come in and undertakes assessment at that point 1 to 1 specialing in place for mental health patients infectious patients nursed by the sink or bed next to the patient is kept empty - area deep cleaned after patient transfer / discharge Queue nurse in place to monitor patients on trolleys in corridors; | Overcrowding of corridors; | Incident reports Ambulance offloading data now included in daily Sitrep; performance and effectiveness of controls reviewed at divisional governance meeting | Ambulance offloading data shows missing targets at times of peak activity | 4 | 4 | 16 | Long term - ED reconfiguration - strategic outline case for capital funding, development underway. target completion date 15.12.15 Short term plan to make immediate smaller scale improvements in development out to tender - target completion date 31 Dec 2015. | 4 | 2 | 8 | 2015-10-14 | F&PC
3577 | PR 7 | Finance |  | Don Richards | 2015-07-29 | Failure to develop and implement sufficient efficiency initiatives to support financial plan Cause: Failure to develop and implement sufficient efficiency initiatives to support financial plan. Effect: Less income and/or more expenditure than planned. Impact: - Failure to meet financial plan targets (£29.2m deficit) Difficulties in making cash available to pay suppliers and staff Reputational damage arising from failing to meet targets. Damaged credibility for long term Trust strategy. | 4 | 4 | 16 | - Structured efficiency programme - Specialist advisory support. - Project plans produced with timescales interdependencies etc. - Performance management system - Quality impact assessment signed off by CMO and Chief Nurse. | Agreed consequences for inadequate performance | Performance reports to Divisional Performance reviews. CFO report to Finance Committee and Board. Reports provided by external advisory firm. TDA performance reviews Internal Audit reports. External Audit reports. | Assurance that poor performance in contributing to the efficiency programme is managed | 4 | 4 | 16 | Ensure that performance in contributing to the efficiency programme is included in staff appraisals (April 2016) | 4 | 2 | 8 | 2015-10-14 | F&PC
3414 | PR 7 | Finance |  | Don Richards | 2015-04-08 | Loss of income resulting from the Trust failing to achieve requirements set out in the CQUIN schedule Loss of income resulting from the Trust failing to achieve requirements set out in the CQUIN schedule | 5 | 4 | 20 | Monthly review of progress against individual CQUINs to identify income effects of any non-compliance. Financial risks for CQUIN revised accordingly and non-compliance escalated to the Executive Team. | Divisional ownership of CQUIN target | Information processed regularly by team that is able to interpret and explain the implications to Divisions and Executive team | Potential delay in CCG feedback on our CQUIN delivery | 5 | 3 | 15 | Ongoing discussions with commissioners highlighting areas of concern. Action plans produced to achieve targets. | 5 | 2 | 10 | 2015-10-14 | F&PC
3420 | PR 7 | Finance |  | Don Richards | 2015-04-08 | There is a risk that the CCG could use the contract levers to penalise the Trust The CCG would be using the contract levers to penalise the Trust for non-performance against nationally and locally mandated targets. This will lead to a loss of income which would worsen the Trust's financial position. This loss will need to be offset by non-recurrent support from the CCG. This non-recurrent support is yet to be agreed. | 5 | 3 | 15 | Ongoing discussions with the CCG to seek clarification regarding re-investment. Trust position made clear to TDA in monthly IDMs | There remains a disconnect between CCG investment of penalties and Trust expectations | Kept on the agenda of QCR meetings and on meetings between CFOs | Disconnect between CCG & Trust priorities | 5 | 3 | 15 | Continue to report our position and escalate to TDA. Ongoing discussions with the CCG to seek clarification regarding re-investment. Kept on the agenda of QCR meetings and on meetings between CFOs Trust position made clear to TDA in monthly IDMs | 5 | 1 | 5 | 2015-10-14 | F&PC
3571 | PR 1 | Corporate | Quality Governance | Helen Brown | 2105-07-29 | Quality and risk management processes insufficiently understood and embedded Cause Understanding of risk management processes insufficiently understood by staff and not embedded into routine practice to ensure that risks to safety, quality, responsiveness and sustainability are systematically identified and managed. Recent examples demonstrate that the system is not working effectively (e.g. theatre ventilation issue). Effect Potential loss of capture of incidents, incidents reported but learning not taken forward to prevent reoccurrence, lack of organisation memory. Risks not appropriately identified, controlled or recorded. Unable to evidence to external regulators that sound processes are in place. Impact Potential detrimental impact on patient pathways and/or care. loss or learning and inability to report accurately and give assurance. April 2015 CQC inspection identified significant shortcomings and key factor in 'inadequate' rating for safe care. Potential negative reputation effects. | 4 | 4 | 16 | Corporate Quality Governance team in place to work with divisions and directorates to improve systems and processes and embed a learning culture. Divisional Quality Governance leads identified. Quality Governance facilitators working in divisions to support divisional governance processes. New Datix system implemented. Concise risk management procedure developed and leaflet for staff. Immediate post CQC action / improvement plan developed. Complaints validation in progress. SI validation maintained.45 day SI reviews initiated. | Governance and Risk Management not fully understood and embedded across the Trust. Process for escalation of incidents and serious incidents not fully embedded across the Trust. RCAs not completed in time in line with SI framework, action plans not always completed with RCA or further tracked to ensure completion and the embedding of learning across the Trust. Delays in responses to complaints. | Monthly Quality and Safety Group (scrutiny) and Quality and Safety sub committee of the board(assurance. Work plan and regular reporting cycle in place. Integrated Performance Report reports key performance indicators for quality and safety and exception report. External review of SI process and 2 days per week expert support secured to implement recommendations. Risk management audit scheduled for Q4. | More structured approach required to ensure core compliance requirements mapped and tracked. IPR and exception reporting needs to be further developed. Detailed Improvement Plan covering all areas quality governance to be developed following receipt of full CQC report. | 4 | 5 | 20 Was 15 | Detailed Quality Governance Improvement plan to be developed as part of overall CQC improvement plan 08.10.15. | 4 | 2 | 8 | 2015-10-14 | SQC
1402 | PR 3 | Environment | Electricity Services | Kevin Howell | 2008-01-30 | All sites - Inadequate Resilience in Power Supply Risk: Electrical infrastructure across 3 sites is ageing with breakdowns increasing in frequency. Recent investment in LV Distribution System has reduced risk but HV Distribution System is in a parlous condition with obsolete equipment operating under restrictions and well beyond its design life. The HV generators on all sites are old and do not provide full cover for all clinical services. Recent failure of an HV transformer at HHH left the site depending on generator supply for 7+ days whilst spares were sourced repairs undertaken. | 4 | 4 | 16 | Generators are in place on all sites to cover essential clinical services. Planned maintenance programme has been developed for all electrical systems. Engineering drawings of electrical distribution systems have been updated. Trust has 3 X Authorised Persons (Electrical) supported by an external Authorising Engineer to ensure all reactive and planned work on electrical systems can be undertaken safely. Electrical failure is included in Major Incident Plan. Trust has exercised clinical contingency plans in event of electrical failure. | Generator supplies only cover Essential Supplies. Over time, as services have 'moved' around the Estate some critical services / functions are now be powered off the non-essential supply. Surgical operations should not be conducted whilst dependent on generator supply. This would have a major impact at WGH if a transformer (or equivalent major component) failed. (Surgical operations would be completed, but new ones would not start) There is no guarantee on the availability of spares due to the age of the equipment. | Backstart tests have been successfully conducted across all sites to test generators and identify services that would not be supplied. Authorising Engineer conducts annual audit of electrical systems to identify significant safety risks. All identified risks to be reviewed at Divisional Governance Group and escalated to Safety & Quality Group where necessary. | Environment Divisional Governance Group and supporting compliance structure will not be in place until 30 Nov 15 | 4 | 4 | 16 Was 15 | HV generator project has been tendered and works should be completed by Autumn 2016. LV Distribution System upgrade project will be completed by end Mar 16. Review of HV distribution system to be completed by end Feb 2016 and works submitted for prioritisation / inclusion in 2016/17 programme. | 4 | 2 | 8 | 2015-10-14 | SQC
2904 | PR 3 | Environment | Estates services | Kevin Howell | 2013-02-13 | Condition of external fabric to buildings - Roofs etc Risk - Fabric of buildings, in particular roofs, are compromised due to age and condition. The resultant water ingress following heavy rainfall is jeopardising the safety of critical infrastructure and the delivery of clinical services. The current rating relates to the known issues in the following areas: 1. Radiology at HHH 2. Data centre at HHH QE Building 3. Shrodells | 4 | 4 | 16 | Repair works have been carried out to highest risk areas (PMoK & WACS roofs at WGH, OMF building at WGH, Theatre 5 & Moynihan Building at SACH and many of the buildings at HHH. Estates provide 24/7 reactive maintenance capability across all sites. Clinical contingency plans exist to cover loss of radiology services at HHH. Remedial works for all areas identified as High Risk are included in 2015/16 backlog maintenance programme. | Monitoring cannot cover all areas. Major investment needed to provide assurance in many of older building - 2ly to be funded as buildings may not have long-term future as healthcare facilities (HHH Radiology, WGH I Block) | Condition survey of Estate, last conducted in Oct 2012, will be updated by end Mar 16. Repairs previously carried out have been monitored during 2015 to ensure repairs are effective. | New leaks will appear each winter due to age of estate and backlog maintenance liability. | 4 | 4 | 16 | Remedial work for Radiology area at HH has been commisioned (August 2015) and work is planned to be complete by mid November 2015. Roof above Data Room at HHH to be inspected in Oct 15 (Prior to onset of winter) to determine effectiveness of remedial work conducted earlier this year. Work on Shrodells roof to be included in capital project for development of Level 3 (to be completed by 31 Mar 16) | 3 | 3 | 9 | 2015-10-14 | SQC
2795 | PR 3 | Environment | Estates services | Kevin Howell | 2011-12-15 | Control of Asbestos Containing Materials (ACMs) Control of Asbestos containing materials (ACMs). ACMs are present throughout the Trust estate, and when managed appropriately provide no risk to patients, staff or visitors and minimum impact on service delivery. Effective management of ACMs is based on the detailed knowledge of where ACMs are present on Trust sites, combined with the ownership and management of a Plan to control all potential ACMs in a manner that ensures they pose no risk to personnel. Between 2011 and early 2015 a number of incidents have arisen that cast doubt on the Trust's ability to provide full assurance with respect to the management of ACMs. These have been the subject of RIDDOR reports, HSE intervention and prosecution. | 3 | 5 | 15 | The Trust has recruited and appointed a Head of Engineering with the necessary training and experience to be appointed as the Responsible Person for Asbestos Management. Re-survey completed of all areas where presence of ACMs could pose risk to Trust staff. Areas which continue to pose risk (identified plantrooms) have restricted access controls in place. Areas identified as contaminated are part of a rolling programme of clearance. There is currently no risk to Trust Staff arising from the presence of ACMs on any of the 3 sites. | There was a potential risk to Estates staff and contractors working in some plantrooms during the periods 2011 - 2015 due to the presence of ACMs. (HR are currently tracing staff (current & ex-employees) that have since left the Trust in order to access the need for additional health surveillance. Although there are no current gaps in controls, the measures in place to control access to some plantrooms are impacting on some aspects of service delivery (delays to theatre ventilation work at SACH, increased time to repair infrastructure (WACS toilets, hot & cold water systems). | Trust has appointed Head of Engineering as the Responsible Person (Asbestos) Reporting through the Environment Division Governance Group to the Safety & Quality Group. New consultant has been engaged to carry out management surveys at all 3 sites, providing project management and expert witness services to the Trust. | Levels of exposure experienced are unknown. Exact number of persons potentially exposed unknown. Access restrictions on some plantrooms may delay reactive maintenance activity, potentially impacting on clinical activity or patient safety. | 3 | 5 | 15 Down from 20 | The Trust is working with the HSE to address all issues arising from previous incidents based on an Action Plan developed in response to the HSE prosecution - to be reviewed first-half of October. During implementation of this Action Plan further gaps in assurance were identified, and a new Management Survey is underway to provide the baseline for revisions to both the Asbestos Management strategy and Plan. This work will be complete by 30 Nov 15. (Mitigation measures, including restricted access to some areas, are in place to ensure patients, staff and visitors are not at risk from ACMs during this period). Funding is allocated in 2015/16 to complete remedial work in plantrooms (by 31 Mar 16). HR are coordinating action relating to any employees (incl contractors) who may have been exposed to ACMs in the period under consideration by the HSE. | 3 | 2 | 6 | 2015-10-14 | SQC
3155 | PR 3 | Medicine | Gastroenterology | Kevin Howell | 2014-07-28 | Failure to deliver the planned expansion of the Endoscopy Unit Failure to deliver the endoscopy expansion plan will result in: -Endoscopy unit not achieving Level A for timeliness of waiting national targets for 3 consecutive months resulting in change to JAG status; -Loss of JAG accreditation leading to loss of reputation, ability to train endoscopists and will lead to loss of our current bowel screening programme (worth £800,000) -Bowel Scope screening unable to expand to running 10 lists by March 2018 (1 list currently running, 1 due to start in Oct 2015 and 1 more to commence in Mar 2016) -Loss of income to the Trust (Income loss calculated to be -Bowel Scope lists on full roll out is £1.8M PA and Symptomatic list income is £2.26M PA) -Inability to meet national targets for symptomatic and suspected cancer patients within national standards -Surveillance cases being pushed out beyond 3 months | 4 | 5 | 20 | Recruited 4 (1 on mat leave) and training in place for nurse endoscopists Nurse Endoscopist starting 01/09/2015 - Band 5 Bowel scope screening list running at Watford; Cystoscopy service has been moved to pre-op assessment Endoscopy expansion plan signed off by the Trust Endoscopy project plan group in place Saturday & Sunday lists running to cope with demand and meet national targets; Staff Interviews for Endoscopy nurses took place w/c 27/07/2015 - 2 recruited & working their notice due to start 1st Sept 15 and the other early Oct 2015. | Endoscopy expansion plan not implemented and no clear Project Plan Job descriptions not matched Increase in number of referrals No space to run additional lists according to plan; Not enough Nurses to cover - links into divisional risk 3062 Still short of a Band 7 | Cystoscopy move confirmed - TLEC Minutes Endoscopy expansion plan signed off Minutes from endoscopy planning group Cancer referral lists | Further work on governance requirements needed - reporting and oversight group/committee. | 4 | 4 | 16 | Endoscopy expansion plan to be implemented to enable endoscopy service to deliver the lists in line with national targets; Actionee - Risk owner, Date - March 2016 Cystoscopy has moved out; options to be discussed with Bruce McFarlane, Kevin Howell & Lynn Hill. Band 7 Recruitment to be actioned; Actionee - Emma Purkis, Consideration being given to outsourcing some surveillance work Earlier start times still being considered | 4 | 2 | 8 | 2015-10-14 | SQC
2883 | PR 3 | Environment | Estates services | Kevin Howell | 2012-01-13 | Legionella and other Bacteria Management and control of water systems Age and poor condition of the infrastructure increases the risk of vulnerable persons becoming infected by Legionella or other bacteria present in the water distribution system. | 4 | 4 | 16 | Risk Assessment undertaken in 2012. Action Plan developed and all highest rated risks mitigated by Backlog maintenance programme in 2013/14 & 2014/15 (tank replacement, deadleg removal and re-engineering of ITU hot and cold water systems). Water Safety Plan, endorsed by Trust in 2013, provided management Action Plan to mitigate all risks to acceptable level. Plan has been implemented and includes water sampling and flushing programmes, TCV maintenance and replacement of calorifiers. Results and remedial action monitored through Water Safety Group and Infection Prevention and Control dashboard. Water sampling in place across Trust including all high risk areas at frequency required in HTM. Robust system in place to mitigate risk from any non-compliance. | There are still some gaps in flushing records. Much of hot and cold water distribution system is old and in need of replacement, increasing risk that bacteria can thrive. Annual Risk Assessment, as required by Water Safety Plan, is overdue - this is an outstanding HSE requirement following HSE Notice of Contravention issued to Trust in December 2013. | Creation of Water Safety Group, reporting through Infection Prevention & Control and Safety & Quality Groups, to provide assurance that management processes are effective. Comprehensive reporting of all results, non-compliance and remedial actions available to DIPC and Chief Microbiologist on Trust intranet. Immediate implementation of contingency plan (including use of point of use filters, flushing and disinfection),when high counts are received. Independent annual audit of Trust water management system by external specialist reporting findings through Water Safety Group. Trust safe system of work complies with HTM requirement. | External audit and risk assessment overdue. Without accurate engineering drawings of water distribution systems full assurance cannot be provided. | 4 | 4 | 16 | Improve reporting of water quality info to IPC. Complete Risk Assessment by end October 2015. Carry out all High & Medium Risk remedial works identified in Risk Assemment by 31 Mar 16. Progress the Water Safety Plan in accordance with programme (ongoing annual requirement). Complete external audit and Risk Assessment by 30 Oct 15. Close out HSE Notice of Contravention by 16 Nov 15. Prioritise investment to close out all High risks identified in Risk Assessment by 31 Mar 16. | 4 | 2 | 8 | 2015-10-14 | SQC
3501 | PR 3 | Environment | Estates services | Kevin Howell | 2015-06-17 | Non-Compliance with HTM 00 - Provision of a Safe System of Work The NHS and HSE requires the Trust to demonstrate that it operates a "Safe System of Work" across its high risk estate management activities. The mandated system is based on suitably trained, skilled and experienced staff at each level within the maintenance organisation; formally appointed to specific identified roles. Demands on the workforce, reliance on Agency staff and removal of the training budget have left the Estates Team unable to meet the level of assurance required by HSE / HTM. Currently less than 50% of the mandated positions required to satisfy HTM 00 are filled by permanent staff. Although the new Estates structure provides basis for full compliance, this will not be achieved until recruitment is complete and all staff are trained and appointed. An external gap analysis identified a lack of evidence that the trust is compliant with the HTM in areas including electrical safety, the management of medical gases, steam, ventilation, pressure and gas systems, lifts, working at heights and in confined spaces. | 4 | 5 | 20 | Head of Engineering has undertaken internal risk assessment to ensure all high risk activities are managed, supervised and undertaken in a safe manner. The new Estates structure, when fully recruited, will provide appropriate management, supervision and expertise at all levels on all 3 sites. Key safety functions (HV, water management, medical gas, pressure systems, gas systems) are currently supported by appropriately skilled external contractors and/or Agency staff. | The current arrangements do not meet the requirements laid down in HTM 00, most specifically the requirement for all appointed Authorised Persons (APs) to have site specific experience. This HTM mandated model is used by the HSE to confirm that a Trust operates a Safe System of Work. | New Environment Division management structure includes provision of monthly compliance audit to Divisional Governance Group. Independent Authorising Engineers provides annual audit of high risk activities, reporting through Divisional Governance Group to Safety & Quality Group. | Divisional Governance Group and supporting compliance structure will not be in plance until 30 Nov 15. Some disciplines (pressure systems, ventilation, working at heights, confined spaces) are not currently subject to external audit. Authorised Persons have not been formally appointed to role. In event of a serious incident involving estates activity, the Trust would not be able to use the HTM mandated model to demonstrate it was operating a safe system of work. | 4 | 4 | 16 Was 15 | Recruit to all vacant posts in Estates & Compliance teams by end Dec 15. Secure training budget for 2016/17 to cover HTM 00 requirements. Expand external audit to cover all high risk activities by 31 Mar 16. Ensure all findings from AE audits are reviewed, within a month, by the Divisional Governance Group, and escalated where necessary to Quality & Safety Group (ongoing requirement). Ensure all essential Authorised Persons, Authorising Engineer and Competent Persons appointments are covered by either Trust staff, Agency or contractors by end Dec 15. Undertake quarterly internal compliance audits, reporting through the Divisional Governance structure to Safety and Quality Group (from 1 Dec 15) In year funding gap for training of Authorised Persons / Competent Persons to be covered from defering planned works to 2016/17. | 4 | 3 | 12 | 2015-10-14 | SQC
3144 | PR 3 | Environment | Estates services | Kevin Howell | 2014-07-21 | Working Environment - Occupational Health, Watford Occupational Health (OH) Department (H-Block Watford General Hospital) The area is currently assessed as unfit for clinical use due to the condition of building, the environment and the space/facilities available. Despite significant investment it has been impossible to stop widespread and invasive damp across the rooms occupied by OH. The environment has been stated as the cause of long-term sickness within the OH staff team. The current area does not meet the minimum mandated requirement for delivery of clinical services (access, infection control, privacy & dignity). | 4 | 5 | 20 | Monitor situation including condition of building fabric (internal and external) and the clinical environment as winter approaches. Identify any short-term remedial work / action that can be undertaken to alleviate mitigate current risk | Lack of suitable area to re-locate the department in the short-term. | Undertake monitoring of air quality to assess potential impact on staff. | Unable to confirm new location for OH or timescale for move. | 4 | 4 | 16 Was 15 | The only mitigation is the relocation of the service. Suitable facilities have been identified on the Watford site, but are subject to conflicting demands. The Interim Estates Strategy, currently in draft form, will confirm the best option. The capital programme may need to be prioritised to facilitate any enabling work. The Plan to relocate OH to be confirmed by 16 Nov 15, and the department will be relocated by 31 Mar 16. This risk will then close. | 4 | 2 | 8 | 2015-10-14 | SQC
2145 | Pr 4 | Clinical Informatics | Data Quality | Lisa Emery | 2009-02-13 | Loss of the Hemel or Watford Data Centres Risk: Data Centres damaged or links to data centres severed. Cause: Physical data centre housing is not fit for purpose therefore risk of damage through fire, water, temperature, humidity, sabotage (physical, virtual), power. Consequences: Prolonged and material loss of IT services hosted from the data centres will seriously hinder WHHT's ability to support the delivery of safe patient care. These services include key clinical and operational IT systems. | 4 | 4 | 16 | 1. Physical security controls in place to restrict access to authorised personal only; 2. Fire suppression systems installed; 3. Mains power supply fed from the site generator and room UPS mitigates interruptions in power during cutover to generator; 4. Some key IT systems are replicated in both data centres; 5. Temperature controls monitored for increases above normal; 6.Make IT Happen application migration will reduce the dependency on the Trust Data Centres | There is only a limited contingency plan in respect of catastrophic system loss. The current situation at the Hemel Data Centre is deteriorating with the roof leak increasing in size and evidence of water in the light fittings and on the airconditioning units | Internal audit reports/NIMS review. Make IT Happen applications migration plan rollout prioritised through Informatics Group. Progress monitored via Informatics Group and F&P Committee | Infrastructure Review/Disaster recovery Plan drafted not yet implemented. | 4 | 4 | 16 | Estates are aware and have instructed contractors to investigate the roof at Hemel. Full repairs are currently underway. Make IT Happen applications migration due to complete January 2016. | 4 | 1 | 4 | 2015-10-14 | SQC
2809 | PR 3 | Environment | Estates services | Kevin Howell | 2012-02-10 | Security Access System The door access system in use at WGH has exceeded its design capacity. Passes issued to new employees, including clinical staff,are not providing access to all areas; creating the possibility that members of the Crash Team may not be able to respond in the necessary timescale. NEW - Escalation Agreed at RRG Setember 2015 | 5 | 3 | 15 | All security access passes are issued by Facilities. Current system ensures that access to 'restricted' areas is only provided to essential staff. System is constantly reviewed and maintained by Facilities & external contractor. | Current system has exceeded capacity, resulting in new pass holders being unable to access assigned areas. Current system cannot be expanded without circa £60k (currently unfunded) capital expenditure. | Current system provides high level of assurance that access to clinical areas is restricted to appropriately assessed personnel only. | Inability to provide assurance that passes issued to personnel arriving in the Trust after 1 Sep 15 creates the possibility that personnel responding to a crash call may not reach the patient in the time necessary to 'treat' the medical emergency. | 5 | 3 | 15 Was 9 | Initiate immediate action to re-designate sufficient cards to guarantee unrestricted card access to all members of the crash team, if necessary by removing lower priority personnel from the system by 18 Sep 15. Initiate capital project to replace current system with robust and future-proofed card access system at WGH by 30 Oct 15. | 5 | 1 | 5 | 2015-10-14 | SQC
3448 | PR 4 | Clinical Support | Radiology | Lisa Emery | 2015-04-13 | PACS Data Storage Cause: The Trust is required to localise the PACS images currently stored at the Accenture Data centre by June 2016. HSCIC has put in place a national process / slot plan to allow for data to be migrated to locally hosted solutions. WHHT ‘slot’ was allocated for August 2015. The plan had been to transfer the data to the Trust’s Outsourced IT partner however they have not been able to provide an appropriate solution within the agreed timeframe. HSCIC require trust to confirm its plan for data migration by 23.09.15 and for transfer to be effected by 1st November 2015. Effect: If the Trust is not able to conform to this requirement there is a risk that migration is not able to be completed within the national timescale resulting in potential for significant loss of patient level clinical data. Impact: Loss of this data will result in potential delays in diagnosis for some patients by preventing review of past imaging, preventing comparison of current and past imaging. This will affect patient care and safety and also presents a medico-legal and financial risk to the Trust. NEW - Escalation Agreed at RRG Setember 2015 | 4 | 3 | 12 | Project manager assigned to this project and urgently investigating alternative local storage solutions in context of failure of original plan. Weekly project team meeting in place. AD, ICT providing senior oversight and support to solution finding. | No firm plan or funding agreed as at 17/09/15. | Escalated to Chief Information Officer and Divisional Director, Clinical support services. Imaging Informatics group provides oversight of project, reporting to Informatics Group. F&P sub committee provides assurance to Board re IM&T risks. | None Identified | 4 | 4 | 16 Was 9 | Urgent review of options, feasibility and costs. Plan to be provided to Accenture by 23.09.15. Update to be provided to F&P on 22.09.15. Funding and procurement solution to be identified and approved (with appropriate waivers if required) by 23.09.15. Identified solution needs to be implemented by 1st November 2015 to ensure data migration slot not missed and minimise risk of data loss. | 4 | 2 | 8 | 2015-10-14 | F&PC
3483 | PR 5 | Medicine | Care of the Elderly | Lynn Hill | 2015-06-11 | Patient Flow, delayed transfers and medical outliers (medicine) Due to the high number of DTOC patients in the hospital, beds are blocked, causing bottlenecks at the front door and queues in A&E leading to long trolley waits, patients not placed on the best ward for their care etc, and the DTOC patients themselves may deteriorate in hospital waiting for onward services. There appears to be a significant lack of capacity in external organisations to be able to manage the flow of patients out of hospital causing the whole process to become slow and congested. | 4 | 5 | 20 | "Automated referral process being trialled to speed up the pathway. Integrated discharge service currently under review to improve the way patients are supported out of hospital Tudor and castle wards are dedicated for patients awaiting care packages Regular SRG meetings to manage the position at Executive level Weekly patient specific review meetings held by the Integrated Discharge Team Weekly operational meeting established between WHHT, HCT and HCC to identify blockages which can be resolved locally " | "Ability to enhance the availability of resources from social care Tudor / Castle wards receiving patients who do not meet cirteria or whose medical condition deteriorates post admission " | System Resilience Group and HCC commitment to reduction - weekly / monthly trend data Incidents Complaints Week on week reduction in DTOCs | DTOC levels remain high | 4 | 4 | 16 | "Robust winter planning for 15/16 to ensure that appropriate surge capacity is available; Review of Configuration of beds to be undertaken and a paper to go to CAG; Need to engage medical & nursing leadership in implementation of standards on all wards as part of the 'perfect ward' roll out plan;" | 4 | 2 | 8 | 2015-10-14 | F&PC
3120 | PR 4 | Medicine | Outpatient Nursing Services | Lynn Hill | 2014-07-09 | Patient Medical Notes missing, Delayed or poor condition. There are a number of issues with the storage, transportation and management of health records in the Trust, which are cumulatively resulting in notes not always being delivered in a timely manner or being available for appointments. The issues are detailed below: a) Space - the Trust has 2 Health Records Libraries, one at WGH and one at HHGH. Due to limited storage space only the records of patients who have attended within the past year are kept on site, with the remainder having to be stored off-site within the secure archive. There is also a significant space issue in Clinic Prep at WGH, as the working environment is overcrowded with insufficent storage, which results in inefficiencies. b) Logistics - notes have to be transported between the 3 sites, which is inefficient and coupled with the existing space issues, often means that the notes for the most acute patients who attend WGH cannot always be stored at WGH Library due to their size (HHGH's Library is larger). c) IG - compliance with the tracking process is poor across the Trust, leading to notes being reported as 'lost' and then being found after intensive searches by the Health Records team. d) Resource - Outpatient activity (which directly impacts the Clinic Prep team) has increased 24% over the past 5 years, with limited review of the Clinic Prep staffing establishment, meaning that the team are having to utlise a high number of bank and agency staff to maintain service which results in instability and decreased efficiency. e) Technology - the Trust does not currently have a strategy for Electronic Patient Records, therefore is not currently harnessing technology that could resolve some of these inefficiencies and therefore improve the patient and clinician experience. | 4 | 5 | 20 | Patient are verbally informed if the notes are missing Nurse staff contact medical records to find required patient records Access to Infloflex to attain limited patient information; | All information not available on infoflex | Incident forms Appointment cancellation due to lack of notes Complaints for cancellation of appointments | Possible breaches in RTT | 4 | 5 | 20 | a) Space - Director of Estates is now working with the Health Records team to identify possible solutions, acknowledging the interdependencies with the Electronic Health Record strategy (see below) and the MRI scanner which will be installed in the WGH Clinic Prep work space by March 2016; b) Logistics / Resource / Technology: The Trust is now working on an Electronic Health Records strategy which will set out the plan for the next 2-5 years and will include proposals to reduce staffing costs and improve efficiency by implementing an effective IT solution. Options include barcoding of records; location-based tracking; scanning of health records; outsourcing of library/prep function; c) Consideration of options to improve medical records tracking, eg tracking by location rather than terminal digits. This is expected to deliver reduced reliance upon additional bank staff, with the potential to release other medical records staff who could be reallocated to clinic preparation duties; d) Clinical Informatics working with Medical Records Department to improve tracking process; e) Business case for move, Sept 15 | 4 | 2 | 8 | 2015-10-14 | F&PC
3422 | PR 2 | Corporate | Human Resources | Paul Da Gama | 2015-04-08 | Engagement within the Trust Cause: Our staff survey tells us that our staff believe that there is poor appraisal compliance, coupled with perceptions of wide spread bullying and harassment and staff shortages at a time of increased patient demand. Effect: Our overall staff engagement is declining year on year and and in a number of areas we are in bottom 20% of Trusts. Issue: This is impacting upon retention and productivity issues. This is manifesting itself in an increasing turnover rate which is requiring increased agency and locum usage, which is negatively impact patient care and creating major fiancial pressures due to increase agency and locum costs | 4 | 5 | 20 | Participation in Listening into Action Programme, which aims to create 'bottom up' change and improvement. Major focus upon ensuring that all colleagues have an appraisal, this figure is now at 81% and improving. New Bullying and Harassment strategy in place, including access to the Bullying & Harassment Advisors have been promoted across the Trust. Value Based Appraisal compliance levels continue to improve. Each division has a local engagement action in place which seeks to address local engagement issues and these plans are reviewed at divisional meetings. Health and well being programme and staff benefits programme relaunched and in operation Leadership development programmes being offered to a range of managers Local presentations of Staff Survey results have taken place, with Divisional action plans in place. | Without addressing fully our recruitment and retention issues low engagement will continue to be an issue for the Trust. It is difficult at this stage to know for certain the likely impact of the recent CQC report upon overall engagement and staff morale. | Each division has a local engagement action in place which seeks to address local engagement issues and these plans are reviewed at divisional meetings. At an organisational level there is regular reporting around key issues impacting engagement e.g. appraisal compliance, B&H figures etc, which is reported upon through: Workforce Performance report. Workforce Committee. Workforce Group. JCC In addition we undertake quarterly Friends and Family surveying and LIA Temperature check | None currently identified | 4 | 4 | 16 | Changes to simplify appraisal processes - Commencing Sept 15 Implementation of B&H Strategy, commencing Sept 15 Launch of new staff benefits programme - during Sept 15 | 4 | 2 | 8 | 2015-10-14 | WFC
3583 | PR 2 | Womens and Children | Gynaecology | Paul Da Gama | 2015-08-05 | High nursing vacancies on Elizabeth Ward leading to poor patient experience, safety risk and financial costs Cause: national workforce shortage, poor staff morale, workload pressures and staff concerns about patient mix, maternity leave Effect: high turnover / poor retention / high vacancy rate (40% vacancy at Band 5) Impact: high usage of bank and agency, risk that not all shifts meet planned nursing workforce levels, adverse impact on quality, safety and patient experience. | 4 | 5 | 20 | - The use of NHSP to try to cover vacant shifts - Manage a/l and sickness as per Trust policy - Ensuring at least one permanent member of staff on each shift - sdaily staffing review and cross cover from otehr departments in line with assessed priorities - temporary closure beds on Elizabeth Ward when overall Trust capacity permits / escalation policy prioritises surgical patients - rolling recruitment to vacant posts and to cover maternity leave | - Inability to obtain staff from other areas because of shortages across the TrustNHSP unable to cover all vacant shifts - current recruitment strategy not effective and needs to be reviewed. | - daily staffing review / safe staffing sit rep and escalation process - safe staffing report to Workforce Group and Workforce submitted | none identified | 4 | 4 | 16 | - targeted workforce strategy & R&R plan to be developed 30.11.15 | 4 | 1 | 4 | 2015-10-14 | WFC
3241 | PR 2 | Medicine | General Medicine & Sub Specialities | Paul Da Gama | 2014-10-17 | High vacancy rates - medical and nursing staff High vacancy rates leading to continued reliance on temporary / agency staff leading to over spend for medical and nursing staffing | 4 | 5 | 20 | HR recruitment Trust weekly meeting | Recruitment - too slow, inability to attract and retain staff Weekly meetings concentrates on patient safety and not financial impact | Financial reports | Increase in agency spend | 4 | 4 | 16 | HR recruitment underway; Overseas recruitment of nurses | 4 | 2 | 8 | 2015-10-14 | WFC
3481 | PR 2 | Unscheduled Care | Emergency Care | Paul Da Gama | 2014-06-11 | Nursing staff in A&E ED nursing vacancy rate. Cause: national skills shortage, workload pressures, environment and trust reputation. Effect: high level of temporary staff use, shortfalls in senior nursing cover vs planned levels, high workload pressure for substantive staff Impact: safety and quality, patient experience, staff morale, financial. | 4 | 5 | 20 | bank and agency cover for vacant shifts. daily review staffing and escalation policy in place. ED workforce strategy / action plan: ongoing R&R, role redesign, ENP training programme | Agency staff may cancel shifts at short notice Unable to cover some shifts at certain times | Staffing review at daily ops meeting; oversight of progress on ED workforce strategy and action plan at Divisional Management Board. safe staffing report to trust board. | to confirm oversight. exception reporting arrangements through to workforce sub committee | 4 | 4 | 16 | Confirm / implement regular update reports on progress against action plan to workforce sub committee of the board. 30.10.15. | 4 | 2 | 8 | 2015-10-14 | WFC
3421 | PR 2 | Corporate | Human Resources | Paul Da Gama | 2015-04-08 | Recruitment and Retention Cause: There is a nationwide shortage of key trainned clinical staff including nurses, A&E consultants, etc. Effect: The Trust is finding it exteremly difficult to recruit to its existing staffing establishment. Impact: The Trust is running with significant levels of vacancies which is impacting on staff morale, leading to even higher levels of turnover, which in turn has the potential to negatively impact patient care and is creating major financial pressures due to increase agency and locum costs. | 4 | 5 | 20 | Recruitment and Retention strategy is in place which includes: Plans for major EU and non-EU overseas recruitment and their integration to the Trust. On-going recruitment in all specialities continues , including large scale cohort recruitment for nursing and HCAs Streamlining of our recruitment processes are Growing our Bank and promoting the organisation. Recruiting our student nurses. Development and succession plans | We need a fit for purpose recruitment website More sustematic promotion and marketing of the organisation More work at a health system level | Weekly Exec led R&R Group driving implementation of the Trust R&R Plan and achievement of related trajectories. Achievement of the R&R plan is reported upon through: Workforce Performance report. Workforce Committee. Workforce Group. JCC Staffing sitrep report is reviewed at staffing review meeting daily Monday to Friday with Chief Nurse. Divisional Performance review meetings led by Deputy CEO. Chief Nurse weekly staffing meetings. | Internally: None currently identified Exetrnally: Recent changes in the Government's requirement for overseas recruitment clearances will have potential significant impact on the Trust achieving the numbers of Filipino nurses planned. | 4 | 5 | 20 | Overseass recuritment in progress – Circa 150 EU nurses due to start with the Trust by December 15. Anticpated that between 20-30 Filippion nurses will start between January - March 16 and then 50 from April 16 onwards. Additional work will need to be undertaken to achieve successful overseas integration into the Trust. This will be in addition to the Trusts normal on going recruitment plans (Oct 15 onwards) Work being undertaken on producing a system wide recruitment and retention plan as part of the Beds and Herts workforce group. (Nov 15) This include advertisements in both the Standard and Metro newspapers (Oct 15) Launch of Trust Recruitment Microsite (Oct 15). | 4 | 2 | 8 | 2015-10-14 | WFC
3227 | PR 2 | Unscheduled Care | Emergency Care | Paul Da Gama | 2014-09-26 | Vacant A&E Consultant posts A&E Medical Staffing Cause: national workforce shortages for emergency medicine, workload pressures, environment, Trust reputation, remuneration and reward packages not competitive compared to elsewhere. Effect: high vacancy rates at consultant and middle grade level leading leading to high use of locum and agency staffing and risk of gaps in senior clincial cover. Places significant pressure on current substantive post holders with adverse impact on morale. Impact: safety and quality, patient experience, delivery of emergency care standards, staff training experience and capacity to undertake clinical governance and service improvement activities. | 4 | 5 | 20 | locum staff to fill vacant shifts substantive consultants filling gaps in rota from SPA / non clinical time. Workforce strategy and action plan developed - skill mix / role redesign / flexible working / training and development packages (ENP, clinical fellow, middle grade training programme, role redesign - e.g. paediatrics and acute medicine with sessional inputs to provide cover to ED). | not always able to secure locum cover for shifts. last minute cancellations. | daily staffing review at operational site meetings with escalation to DD and MD. progress against action plan delivery monitored via divisional board meeting and bi-monthly updates to workforce committee. | monthly / trend reporting ref gaps in cover. variable use of datix to record gaps in cover. | 4 | 4 | 16 | Action plan to be reviewed monthly at divisional board and bi-monthly at workforce committee. Monthly reporting of medical staffing gaps in cover to be developed (trust wide)30.11.15 | 4 | 2 | 8 | 2015-10-14 | WFC
3585 | PR 2 | Corporate | Human Resources | Paul Da Gama | 2015-04-08 | Trust's ability to secure temporary staff through NHSP/Locum Booking procedures are inconsistent. Cause: Due to national staff shortages, coupled with issues with the service provided by NHSP, as well major competition from nursing agencies our staff Bank is unable to provide us with the required level of service Effect: Our Bank to agency ratio has declined from 35%-55% to 25%-60% and our unfill rate has increased. Impact: This has lead to increased agency costs and impacted upon fill rates for nursing shifts. Overall there is wide spread organisational concern around the service provided by NHSP. NEW - Escalation Agreed at RRG Setember 2015 | 4 | 5 | 20 | We have launch a formal dispute with NHSP regarding their service and in particular their inability to grow and maintain our staff bank. Following a meeting with two of their senior Directors it was agreed that they would create a relaunch plan which would include work on the following: • Plans to strategically build our bank including for example their providing us with overseas nurses as part of our bank on Bank only contracts • New and improved reporting • Agreed SLAs • Formally agreed and contractually binding KPIs • New local line management • Assistance with our approach to rota management and demand management • Improved on-site presence by NHSP staff In addition propsals have been put forward around reviewing our current Bank rates. | Strategic plan to grow Bank NHSP Re-launch plan Formally agreed KPIs around NHSP's service System wide agreement around Bank rates | Fortnightly senior meetings between NHSP and the Trust where performance figures are reviews Weekly bank/Agency reports. At an organisational level there is regular reporting around agency/Bank usage which is reported upon through: Workforce Performance report. Workforce Committee. Workforce Group. JCC | None identified | 4 | 5 | 20 Was 9 | Bank Re-launch plan - Oct 15 Review of Bank rates - Sept 15 Overseas nurse recruitment - Dec 15 | 4 | 2 | 8 | 2015-10-14 | WFC
3513 | PR 2 | Womens and Children | Obstetrics | Tracey Carter | 2015-07-17 | Poor Team Working and Engagement Potential conflict and poor communication within the Divisional Obstetric Team Cause: Maternity professional staff relationships are poor. Effect: Poor team working across maternity services and the need for improved working relationships (especially labour ward and theatres).Poor staff morale, poor recuritment and retention, high turnover. Impact: staffing shortfalls, quality and safety, patient experince, financial impact | 4 | 5 | 20 | 1. Closure of provate obstetrics 2. Listening Exercise about Obs & Gynae Theatre Staff commissioned by Chief Nurse and Lead Nurse for Surgery - Completed 3. New medical leadership - external AMD for O&G appointed and providing 2 days per week clinical leadership. New Clinical Director appointment across Obstetrics and Gynaecology. 4. Consultant Labour Ward lead recruited to commence September 2015. Consultant 'hot days' for consultant cover on Delivery Suite agreed to commence on 01/09/15 5. Substantive Matron in Delivery Suite recruited 6. Recruitment and Retention strategy developed. 7. Joint women and childrens theatres 'onion' meeting convened | 1. Not all staff are due to start immediately and results of listening exercise are not yet available 2. No formalised action plan is yet in place | 1. 'Listening into Action' and providing staff with opportunity to tell CE about work related frustrations 2. Staff survey 3. Maternity dashboard 4. Maternity Friends and Family Test 5. Divisional Management Group 6. Quality and Safty updates to QSG and Q&S committee. | 1. targeted maternity specific 'staff temperature check' not yet implemented | 4 | 4 | 16 | 1. Developing action plan to address findings of listening exercise for approval by TEC - 30.09.15 2. first staff temperature check for maternity undertaken - 31.11.15 | MINOR | 2 | 4 | 2015-10-14 | WFC
3512 | PR 2 | Womens and Children | Neonatal Intensive Care Unit | Tracey Carter | 2015-07-17 | Neonatal Nursing Establishment Cause: Neonatal nursing establishment is below level recommended by BAPM Effect: insufficient substantive qualified neonatal nurses available to ensure all shifts fulfil expected staffing requirement (ie vs assessed level of demand and acuity on a shift by shift basis) Impact: potential adverse impact safety, patient experience, staff morale and reputational damage. | 4 | 4 | 16 | Temporary staff booked in order to meet safety requirements and BAPM standards. Staffing levels monitored daily and reported on Trust sit rep. joint daily ward round with maternity services to identify potential demand for neonatal care and support workforce planning. Escalation policy in place including if required diversion of high risk women in labour if unit staffing assessed as unsafe. | - Inability to fill temporary staff requests at short notice | - Deficits in nursing reported onto Datix. - incidents reviewed at neonatal quality and safety governance group | - review trend data | 4 | 4 | 16 | Establishment review completed June 2015, presented to TLEC July 2015. Business case for 6.0 wte increase in nursing establishment to be developed for TEC approval. 30.10.15 | 4 | 2 | 8 | 2015-10-14 | WFC
3277 | PR 3 | Womens and Children | Paediatrics | Tracey Carter | 2014-11-11 | Safety and Security No Tagging Alarms Cause: building layout and inherent challenges of maintaining fully secure environment in hospital setting Effect: risk of unauthorised persons gaining access to maternity and neonatal wards and departments presenting a security risk for paitents and staff and potential risk of abduction of newborn baby or child Impact: patient and staff safety. | 5 | 4 | 20 | Annual risk assessments undertaken for all areas controlled door entry systems in place Security cameras in place Security of newborn child policy On site security | Security under review. | Datix reporting Quality and Safet Group and Committee | None identified | 5 | 3 | 15 | Updated risk assessment commissioned from local security manager by Chief Nurse - to be completed by 30.09.15 | 5 | 1 | 5 | 2015-10-14 | F&PC

## Escalated Risks not Agreed (1)
ID | Principle Risk | Division | Speciality | Risk Lead/Exec Lead | Opened | Description | Consequence (initial) | Likelihood (initial) | Rating (initial) | Controls | Gaps in controls | Assurances | Gaps in assurances | Consequence (current) | Likelihood (current) | Rating (current) | Action Plan Summary | Consequence (Target) | Likelihood (Target) | Rating (Target) | Risk Review Date | Board Committee | Action Following RRG Review if not escalated
3578 | PR 7 | Finance |  | Don Richards | 2015-07-29 | Cause: Failure to control net income and expenditure within amounts budgeted for in Annual Plan due to either more activity than planned or poor budgetary control. Effect: Less income and/or more expenditure than planned. Impact: Failure to meet financial plan targets Difficulties in making cash available to pay suppliers and staff Reputational damage arising from failing to meet targets. Damaged credibility for long term Trust strategy. | 4 | 4 | 16 | Financial planning process produced by CFO and agreed by Trust. Financial plan and Budgets signed off by Divisional management and the Board. Standing Financial Instructions. Detailed financial controls framework in place. Electronic purchase to pay system used. Regular statements issued to managers, providing information on performance against plan. Finance manager production of analyses and issued to Managers. Contractual payment rules. Business case approval process to allow investment linked to increased patient activity. | Agreed consequences for inadequate performance. Controls over management of sudden unscheduled increases in demand not covered by increased contractual income. | Performance reports to Divisional Performance reviews. CFO reports to Finance Committee and Board. Internal Audit reports. External Audit reports. Control account and other financial reconciliation independently audited. TDA performance reviews. Signed contracts approved by Board. | Assurance that action is being taken to manage poor budgetary control performance Assurance regarding acceptable variation to clinical practice to support efficiency. Assurance that agreed processes for securing temporary staff | 4 | 4 | 16 | Further development of the Trust’s patient level costing and service line reporting to provide assurance regarding acceptable variation to practice. (Timetable contained within paper to Finance Committee). Reports on compliance with temporary staff deployment procedures are being satisfactorily complied with. | 4 | 2 | 8 | 2015-10-14 | F&PC | Further Work Requested on description and scoring. HB to work with DR ahead of next RRG in October 15.

## Principle Risk Summary
Principal | Principal | Principal | CRR (27) Risks | Description | Executive Leads | Board assurance ?
Objective | Aim | Risk | Mapped
PO1 | 1a, 2a, 3 | PR1 | 1 | Quality governance and risk management processes insufficiently robust and embedded, compromising ability to provide safe, effective care and health and safety of staff and visitors | HB | SQC
PO1 | 1a, 2a, 3, 5a | PR2 | 9 | Failure to recruit to full establishments, retain and engage workforce | PDG / TC | WFC
PO1 | 1b | PR3 | 10 | Current estate and infrastructure compromises ability to deliver safe, responsive and efficient patient care | KH | QSC
PO1 | 2b | PR4 | 3 | Underdeveloped informatics infrastructure compromises ability to deliver safe, responsive and efficient patient care | LE | F&P
PO1 | 4 | PR5 | 1 | Inability to deliver and maintain performance standards | LH, CL | F&P
PO1 | 1a,2a,3, 4 | PR6 | 0 | Under developed business continuity plans | HB / KH | SQC
PO1, PO3 | 5b | PR7 | 3 | Failure to achieve financial targets, maintain financial control and realise and sustain benefits from CIP and Efficiency Programmes | DR | F&P
PO1, PO2, PO3 | 1a, | PR8 | 0 | Failure to sustain key external stakeholder relationships and communications compromises the organisation’s strategic position and reputation
PO2, PO3 | 5d | PR9 | 0 | Insufficient focus and organisational capacity directed at the development of the long term clinical, financial and estates strategy

## CRR By Principle Risk
ID | Principle Risk | Division | Speciality | Risk Lead/Exec Lead | Opened | Description | Consequence (initial) | Likelihood (initial) | Rating (initial) | Controls | Gaps in controls | Assurances | Gaps in assurances | Consequence (current) | Likelihood (current) | Rating (current) | Action Plan Summary | Consequence (Target) | Likelihood (Target) | Rating (Target) | Risk Review Date | Board Committee
3571 | PR 1 | Corporate | Quality Governance | Helen Brown | 2105-07-29 | Quality and risk management processes insufficiently understood and embedded Cause Understanding of risk management processes insufficiently understood by staff and not embedded into routine practice to ensure that risks to safety, quality, responsiveness and sustainability are systematically identified and managed. Recent examples demonstrate that the system is not working effectively (e.g. theatre ventilation issue). Effect Potential loss of capture of incidents, incidents reported but learning not taken forward to prevent reoccurrence, lack of organisation memory. Risks not appropriately identified, controlled or recorded. Unable to evidence to external regulators that sound processes are in place. Impact Potential detrimental impact on patient pathways and/or care. loss or learning and inability to report accurately and give assurance. April 2015 CQC inspection identified significant shortcomings and key factor in 'inadequate' rating for safe care. Potential negative reputation effects. | 4 | 4 | 16 | Corporate Quality Governance team in place to work with divisions and directorates to improve systems and processes and embed a learning culture. Divisional Quality Governance leads identified. Quality Governance facilitators working in divisions to support divisional governance processes. New Datix system implemented. Concise risk management procedure developed and leaflet for staff. Immediate post CQC action / improvement plan developed. Complaints validation in progress. SI validation maintained.45 day SI reviews initiated. | Governance and Risk Management not fully understood and embedded across the Trust. Process for escalation of incidents and serious incidents not fully embedded across the Trust. RCAs not completed in time in line with SI framework, action plans not always completed with RCA or further tracked to ensure completion and the embedding of learning across the Trust. Delays in responses to complaints. | Monthly Quality and Safety Group (scrutiny) and Quality and Safety sub committee of the board(assurance. Work plan and regular reporting cycle in place. Integrated Performance Report reports key performance indicators for quality and safety and exception report. External review of SI process and 2 days per week expert support secured to implement recommendations. Risk management audit scheduled for Q4. | More structured approach required to ensure core compliance requirements mapped and tracked. IPR and exception reporting needs to be further developed. Detailed Improvement Plan covering all areas quality governance to be developed following receipt of full CQC report. | 4 | 5 | 20 Was 15 | Detailed Quality Governance Improvement plan to be developed as part of overall CQC improvement plan 08.10.15. | 4 | 2 | 8 | 2015-10-14 | SQC
3422 | PR 2 | Corporate | Human Resources | Paul Da Gama | 2015-04-08 | Engagement within the Trust Cause: Our staff survey tells us that our staff believe that there is poor appraisal compliance, coupled with perceptions of wide spread bullying and harassment and staff shortages at a time of increased patient demand. Effect: Our overall staff engagement is declining year on year and and in a number of areas we are in bottom 20% of Trusts. Issue: This is impacting upon retention and productivity issues. This is manifesting itself in an increasing turnover rate which is requiring increased agency and locum usage, which is negatively impact patient care and creating major fiancial pressures due to increase agency and locum costs | 4 | 5 | 20 | Participation in Listening into Action Programme, which aims to create 'bottom up' change and improvement. Major focus upon ensuring that all colleagues have an appraisal, this figure is now at 81% and improving. New Bullying and Harassment strategy in place, including access to the Bullying & Harassment Advisors have been promoted across the Trust. Value Based Appraisal compliance levels continue to improve. Each division has a local engagement action in place which seeks to address local engagement issues and these plans are reviewed at divisional meetings. Health and well being programme and staff benefits programme relaunched and in operation Leadership development programmes being offered to a range of managers Local presentations of Staff Survey results have taken place, with Divisional action plans in place. | Without addressing fully our recruitment and retention issues low engagement will continue to be an issue for the Trust. It is difficult at this stage to know for certain the likely impact of the recent CQC report upon overall engagement and staff morale. | Each division has a local engagement action in place which seeks to address local engagement issues and these plans are reviewed at divisional meetings. At an organisational level there is regular reporting around key issues impacting engagement e.g. appraisal compliance, B&H figures etc, which is reported upon through: Workforce Performance report. Workforce Committee. Workforce Group. JCC In addition we undertake quarterly Friends and Family surveying and LIA Temperature check | None currently identified | 4 | 4 | 16 | Changes to simplify appraisal processes - Commencing Sept 15 Implementation of B&H Strategy, commencing Sept 15 Launch of new staff benefits programme - during Sept 15 | 4 | 2 | 8 | 2015-10-14 | WFC
3583 | PR 2 | Womens and Children | Gynaecology | Paul Da Gama | 2015-08-05 | High nursing vacancies on Elizabeth Ward leading to poor patient experience, safety risk and financial costs Cause: national workforce shortage, poor staff morale, workload pressures and staff concerns about patient mix, maternity leave Effect: high turnover / poor retention / high vacancy rate (40% vacancy at Band 5) Impact: high usage of bank and agency, risk that not all shifts meet planned nursing workforce levels, adverse impact on quality, safety and patient experience. | 4 | 5 | 20 | - The use of NHSP to try to cover vacant shifts - Manage a/l and sickness as per Trust policy - Ensuring at least one permanent member of staff on each shift - sdaily staffing review and cross cover from otehr departments in line with assessed priorities - temporary closure beds on Elizabeth Ward when overall Trust capacity permits / escalation policy prioritises surgical patients - rolling recruitment to vacant posts and to cover maternity leave | - Inability to obtain staff from other areas because of shortages across the TrustNHSP unable to cover all vacant shifts - current recruitment strategy not effective and needs to be reviewed. | - daily staffing review / safe staffing sit rep and escalation process - safe staffing report to Workforce Group and Workforce submitted | none identified | 4 | 4 | 16 | - targeted workforce strategy & R&R plan to be developed 30.11.15 | 4 | 1 | 4 | 2015-10-14 | WFC
3241 | PR 2 | Medicine | General Medicine & Sub Specialities | Paul Da Gama | 2014-10-17 | High vacancy rates - medical and nursing staff High vacancy rates leading to continued reliance on temporary / agency staff leading to over spend for medical and nursing staffing | 4 | 5 | 20 | HR recruitment Trust weekly meeting | Recruitment - too slow, inability to attract and retain staff Weekly meetings concentrates on patient safety and not financial impact | Financial reports | Increase in agency spend | 4 | 4 | 16 | HR recruitment underway; Overseas recruitment of nurses | 4 | 2 | 8 | 2015-10-14 | WFC
3481 | PR 2 | Unscheduled Care | Emergency Care | Paul Da Gama | 2014-06-11 | Nursing staff in A&E ED nursing vacancy rate. Cause: national skills shortage, workload pressures, environment and trust reputation. Effect: high level of temporary staff use, shortfalls in senior nursing cover vs planned levels, high workload pressure for substantive staff Impact: safety and quality, patient experience, staff morale, financial. | 4 | 5 | 20 | bank and agency cover for vacant shifts. daily review staffing and escalation policy in place. ED workforce strategy / action plan: ongoing R&R, role redesign, ENP training programme | Agency staff may cancel shifts at short notice Unable to cover some shifts at certain times | Staffing review at daily ops meeting; oversight of progress on ED workforce strategy and action plan at Divisional Management Board. safe staffing report to trust board. | to confirm oversight. exception reporting arrangements through to workforce sub committee | 4 | 4 | 16 | Confirm / implement regular update reports on progress against action plan to workforce sub committee of the board. 30.10.15. | 4 | 2 | 8 | 2015-10-14 | WFC
3421 | PR 2 | Corporate | Human Resources | Paul Da Gama | 2015-04-08 | Recruitment and Retention Cause: There is a nationwide shortage of key trainned clinical staff including nurses, A&E consultants, etc. Effect: The Trust is finding it exteremly difficult to recruit to its existing staffing establishment. Impact: The Trust is running with significant levels of vacancies which is impacting on staff morale, leading to even higher levels of turnover, which in turn has the potential to negatively impact patient care and is creating major financial pressures due to increase agency and locum costs. | 4 | 5 | 20 | Recruitment and Retention strategy is in place which includes: Plans for major EU and non-EU overseas recruitment and their integration to the Trust. On-going recruitment in all specialities continues , including large scale cohort recruitment for nursing and HCAs Streamlining of our recruitment processes are Growing our Bank and promoting the organisation. Recruiting our student nurses. Development and succession plans | We need a fit for purpose recruitment website More sustematic promotion and marketing of the organisation More work at a health system level | Weekly Exec led R&R Group driving implementation of the Trust R&R Plan and achievement of related trajectories. Achievement of the R&R plan is reported upon through: Workforce Performance report. Workforce Committee. Workforce Group. JCC Staffing sitrep report is reviewed at staffing review meeting daily Monday to Friday with Chief Nurse. Divisional Performance review meetings led by Deputy CEO. Chief Nurse weekly staffing meetings. | Internally: None currently identified Exetrnally: Recent changes in the Government's requirement for overseas recruitment clearances will have potential significant impact on the Trust achieving the numbers of Filipino nurses planned. | 4 | 5 | 20 | Overseass recuritment in progress – Circa 150 EU nurses due to start with the Trust by December 15. Anticpated that between 20-30 Filippion nurses will start between January - March 16 and then 50 from April 16 onwards. Additional work will need to be undertaken to achieve successful overseas integration into the Trust. This will be in addition to the Trusts normal on going recruitment plans (Oct 15 onwards) Work being undertaken on producing a system wide recruitment and retention plan as part of the Beds and Herts workforce group. (Nov 15) This include advertisements in both the Standard and Metro newspapers (Oct 15) Launch of Trust Recruitment Microsite (Oct 15). | 4 | 2 | 8 | 2015-10-14 | WFC
3227 | PR 2 | Unscheduled Care | Emergency Care | Paul Da Gama | 2014-09-26 | Vacant A&E Consultant posts A&E Medical Staffing Cause: national workforce shortages for emergency medicine, workload pressures, environment, Trust reputation, remuneration and reward packages not competitive compared to elsewhere. Effect: high vacancy rates at consultant and middle grade level leading leading to high use of locum and agency staffing and risk of gaps in senior clincial cover. Places significant pressure on current substantive post holders with adverse impact on morale. Impact: safety and quality, patient experience, delivery of emergency care standards, staff training experience and capacity to undertake clinical governance and service improvement activities. | 4 | 5 | 20 | locum staff to fill vacant shifts substantive consultants filling gaps in rota from SPA / non clinical time. Workforce strategy and action plan developed - skill mix / role redesign / flexible working / training and development packages (ENP, clinical fellow, middle grade training programme, role redesign - e.g. paediatrics and acute medicine with sessional inputs to provide cover to ED). | not always able to secure locum cover for shifts. last minute cancellations. | daily staffing review at operational site meetings with escalation to DD and MD. progress against action plan delivery monitored via divisional board meeting and bi-monthly updates to workforce committee. | monthly / trend reporting ref gaps in cover. variable use of datix to record gaps in cover. | 4 | 4 | 16 | Action plan to be reviewed monthly at divisional board and bi-monthly at workforce committee. Monthly reporting of medical staffing gaps in cover to be developed (trust wide)30.11.15 | 4 | 2 | 8 | 2015-10-14 | WFC
3585 | PR 2 | Corporate | Human Resources | Paul Da Gama | 2015-04-08 | Trust's ability to secure temporary staff through NHSP/Locum Booking procedures are inconsistent. Cause: Due to national staff shortages, coupled with issues with the service provided by NHSP, as well major competition from nursing agencies our staff Bank is unable to provide us with the required level of service Effect: Our Bank to agency ratio has declined from 35%-55% to 25%-60% and our unfill rate has increased. Impact: This has lead to increased agency costs and impacted upon fill rates for nursing shifts. Overall there is wide spread organisational concern around the service provided by NHSP. NEW - Escalation Agreed at RRG Setember 2015 | 4 | 5 | 20 | We have launch a formal dispute with NHSP regarding their service and in particular their inability to grow and maintain our staff bank. Following a meeting with two of their senior Directors it was agreed that they would create a relaunch plan which would include work on the following: • Plans to strategically build our bank including for example their providing us with overseas nurses as part of our bank on Bank only contracts • New and improved reporting • Agreed SLAs • Formally agreed and contractually binding KPIs • New local line management • Assistance with our approach to rota management and demand management • Improved on-site presence by NHSP staff In addition propsals have been put forward around reviewing our current Bank rates. | Strategic plan to grow Bank NHSP Re-launch plan Formally agreed KPIs around NHSP's service System wide agreement around Bank rates | Fortnightly senior meetings between NHSP and the Trust where performance figures are reviews Weekly bank/Agency reports. At an organisational level there is regular reporting around agency/Bank usage which is reported upon through: Workforce Performance report. Workforce Committee. Workforce Group. JCC | None identified | 4 | 5 | 20 Was 9 | Bank Re-launch plan - Oct 15 Review of Bank rates - Sept 15 Overseas nurse recruitment - Dec 15 | 4 | 2 | 8 | 2015-10-14 | WFC
3513 | PR 2 | Womens and Children | Obstetrics | Tracey Carter | 2015-07-17 | Poor Team Working and Engagement Potential conflict and poor communication within the Divisional Obstetric Team Cause: Maternity professional staff relationships are poor. Effect: Poor team working across maternity services and the need for improved working relationships (especially labour ward and theatres).Poor staff morale, poor recuritment and retention, high turnover. Impact: staffing shortfalls, quality and safety, patient experince, financial impact | 4 | 5 | 20 | 1. Closure of provate obstetrics 2. Listening Exercise about Obs & Gynae Theatre Staff commissioned by Chief Nurse and Lead Nurse for Surgery - Completed 3. New medical leadership - external AMD for O&G appointed and providing 2 days per week clinical leadership. New Clinical Director appointment across Obstetrics and Gynaecology. 4. Consultant Labour Ward lead recruited to commence September 2015. Consultant 'hot days' for consultant cover on Delivery Suite agreed to commence on 01/09/15 5. Substantive Matron in Delivery Suite recruited 6. Recruitment and Retention strategy developed. 7. Joint women and childrens theatres 'onion' meeting convened | 1. Not all staff are due to start immediately and results of listening exercise are not yet available 2. No formalised action plan is yet in place | 1. 'Listening into Action' and providing staff with opportunity to tell CE about work related frustrations 2. Staff survey 3. Maternity dashboard 4. Maternity Friends and Family Test 5. Divisional Management Group 6. Quality and Safty updates to QSG and Q&S committee. | 1. targeted maternity specific 'staff temperature check' not yet implemented | 4 | 4 | 16 | 1. Developing action plan to address findings of listening exercise for approval by TEC - 30.09.15 2. first staff temperature check for maternity undertaken - 31.11.15 | MINOR | 2 | 4 | 2015-10-14 | WFC
3512 | PR 2 | Womens and Children | Neonatal Intensive Care Unit | Tracey Carter | 2015-07-17 | Neonatal Nursing Establishment Cause: Neonatal nursing establishment is below level recommended by BAPM Effect: insufficient substantive qualified neonatal nurses available to ensure all shifts fulfil expected staffing requirement (ie vs assessed level of demand and acuity on a shift by shift basis) Impact: potential adverse impact safety, patient experience, staff morale and reputational damage. | 4 | 4 | 16 | Temporary staff booked in order to meet safety requirements and BAPM standards. Staffing levels monitored daily and reported on Trust sit rep. joint daily ward round with maternity services to identify potential demand for neonatal care and support workforce planning. Escalation policy in place including if required diversion of high risk women in labour if unit staffing assessed as unsafe. | - Inability to fill temporary staff requests at short notice | - Deficits in nursing reported onto Datix. - incidents reviewed at neonatal quality and safety governance group | - review trend data | 4 | 4 | 16 | Establishment review completed June 2015, presented to TLEC July 2015. Business case for 6.0 wte increase in nursing establishment to be developed for TEC approval. 30.10.15 | 4 | 2 | 8 | 2015-10-14 | WFC
3480 | PR 3 | Unscheduled Care | Emergency Care | Caroline Landon | 2015-06-11 | A&E Estates Due to the layout / size of A&E department and increase in activity, the A&E dept: 1. lacks space to offload ambulances leading to queues in the corridor; 2. Isolate infectious patients 3. Non compliant with Royal Society of Psychiatrists for a suitable / safe mental health room 4. lack of space for triage (initial assessment for clinicians) 5. May possibly breach single sex accomodation in CDU this has an adverse impact on the quality and saftey of the service, working environment for staff and efficiency / ability to meet key performance targets. | 4 | 5 | 20 | Reduced number of bays in CDU to avoid single sex breaches RGN sits in with reception staff when patients come in and undertakes assessment at that point 1 to 1 specialing in place for mental health patients infectious patients nursed by the sink or bed next to the patient is kept empty - area deep cleaned after patient transfer / discharge Queue nurse in place to monitor patients on trolleys in corridors; | Overcrowding of corridors; | Incident reports Ambulance offloading data now included in daily Sitrep; performance and effectiveness of controls reviewed at divisional governance meeting | Ambulance offloading data shows missing targets at times of peak activity | 4 | 4 | 16 | Long term - ED reconfiguration - strategic outline case for capital funding, development underway. target completion date 15.12.15 Short term plan to make immediate smaller scale improvements in development out to tender - target completion date 31 Dec 2015. | 4 | 2 | 8 | 2015-10-14 | F&PC
3277 | PR 3 | Womens and Children | Paediatrics | Tracey Carter | 2014-11-11 | Safety and Security No Tagging Alarms Cause: building layout and inherent challenges of maintaining fully secure environment in hospital setting Effect: risk of unauthorised persons gaining access to maternity and neonatal wards and departments presenting a security risk for paitents and staff and potential risk of abduction of newborn baby or child Impact: patient and staff safety. | 5 | 4 | 20 | Annual risk assessments undertaken for all areas controlled door entry systems in place Security cameras in place Security of newborn child policy On site security | Security under review. | Datix reporting Quality and Safet Group and Committee | None identified | 5 | 3 | 15 | Updated risk assessment commissioned from local security manager by Chief Nurse - to be completed by 30.09.15 | 5 | 1 | 5 | 2015-10-14 | F&PC
1402 | PR 3 | Environment | Electricity Services | Kevin Howell | 2008-01-30 | All sites - Inadequate Resilience in Power Supply Risk: Electrical infrastructure across 3 sites is ageing with breakdowns increasing in frequency. Recent investment in LV Distribution System has reduced risk but HV Distribution System is in a parlous condition with obsolete equipment operating under restrictions and well beyond its design life. The HV generators on all sites are old and do not provide full cover for all clinical services. Recent failure of an HV transformer at HHH left the site depending on generator supply for 7+ days whilst spares were sourced repairs undertaken. | 4 | 4 | 16 | Generators are in place on all sites to cover essential clinical services. Planned maintenance programme has been developed for all electrical systems. Engineering drawings of electrical distribution systems have been updated. Trust has 3 X Authorised Persons (Electrical) supported by an external Authorising Engineer to ensure all reactive and planned work on electrical systems can be undertaken safely. Electrical failure is included in Major Incident Plan. Trust has exercised clinical contingency plans in event of electrical failure. | Generator supplies only cover Essential Supplies. Over time, as services have 'moved' around the Estate some critical services / functions are now be powered off the non-essential supply. Surgical operations should not be conducted whilst dependent on generator supply. This would have a major impact at WGH if a transformer (or equivalent major component) failed. (Surgical operations would be completed, but new ones would not start) There is no guarantee on the availability of spares due to the age of the equipment. | Backstart tests have been successfully conducted across all sites to test generators and identify services that would not be supplied. Authorising Engineer conducts annual audit of electrical systems to identify significant safety risks. All identified risks to be reviewed at Divisional Governance Group and escalated to Safety & Quality Group where necessary. | Environment Divisional Governance Group and supporting compliance structure will not be in place until 30 Nov 15 | 4 | 4 | 16 Was 15 | HV generator project has been tendered and works should be completed by Autumn 2016. LV Distribution System upgrade project will be completed by end Mar 16. Review of HV distribution system to be completed by end Feb 2016 and works submitted for prioritisation / inclusion in 2016/17 programme. | 4 | 2 | 8 | 2015-10-14 | SQC
2904 | PR 3 | Environment | Estates services | Kevin Howell | 2013-02-13 | Condition of external fabric to buildings - Roofs etc Risk - Fabric of buildings, in particular roofs, are compromised due to age and condition. The resultant water ingress following heavy rainfall is jeopardising the safety of critical infrastructure and the delivery of clinical services. The current rating relates to the known issues in the following areas: 1. Radiology at HHH 2. Data centre at HHH QE Building 3. Shrodells | 4 | 4 | 16 | Repair works have been carried out to highest risk areas (PMoK & WACS roofs at WGH, OMF building at WGH, Theatre 5 & Moynihan Building at SACH and many of the buildings at HHH. Estates provide 24/7 reactive maintenance capability across all sites. Clinical contingency plans exist to cover loss of radiology services at HHH. Remedial works for all areas identified as High Risk are included in 2015/16 backlog maintenance programme. | Monitoring cannot cover all areas. Major investment needed to provide assurance in many of older building - 2ly to be funded as buildings may not have long-term future as healthcare facilities (HHH Radiology, WGH I Block) | Condition survey of Estate, last conducted in Oct 2012, will be updated by end Mar 16. Repairs previously carried out have been monitored during 2015 to ensure repairs are effective. | New leaks will appear each winter due to age of estate and backlog maintenance liability. | 4 | 4 | 16 | Remedial work for Radiology area at HH has been commisioned (August 2015) and work is planned to be complete by mid November 2015. Roof above Data Room at HHH to be inspected in Oct 15 (Prior to onset of winter) to determine effectiveness of remedial work conducted earlier this year. Work on Shrodells roof to be included in capital project for development of Level 3 (to be completed by 31 Mar 16) | 3 | 3 | 9 | 2015-10-14 | SQC
2795 | PR 3 | Environment | Estates services | Kevin Howell | 2011-12-15 | Control of Asbestos Containing Materials (ACMs) Control of Asbestos containing materials (ACMs). ACMs are present throughout the Trust estate, and when managed appropriately provide no risk to patients, staff or visitors and minimum impact on service delivery. Effective management of ACMs is based on the detailed knowledge of where ACMs are present on Trust sites, combined with the ownership and management of a Plan to control all potential ACMs in a manner that ensures they pose no risk to personnel. Between 2011 and early 2015 a number of incidents have arisen that cast doubt on the Trust's ability to provide full assurance with respect to the management of ACMs. These have been the subject of RIDDOR reports, HSE intervention and prosecution. | 3 | 5 | 15 | The Trust has recruited and appointed a Head of Engineering with the necessary training and experience to be appointed as the Responsible Person for Asbestos Management. Re-survey completed of all areas where presence of ACMs could pose risk to Trust staff. Areas which continue to pose risk (identified plantrooms) have restricted access controls in place. Areas identified as contaminated are part of a rolling programme of clearance. There is currently no risk to Trust Staff arising from the presence of ACMs on any of the 3 sites. | There was a potential risk to Estates staff and contractors working in some plantrooms during the periods 2011 - 2015 due to the presence of ACMs. (HR are currently tracing staff (current & ex-employees) that have since left the Trust in order to access the need for additional health surveillance. Although there are no current gaps in controls, the measures in place to control access to some plantrooms are impacting on some aspects of service delivery (delays to theatre ventilation work at SACH, increased time to repair infrastructure (WACS toilets, hot & cold water systems). | Trust has appointed Head of Engineering as the Responsible Person (Asbestos) Reporting through the Environment Division Governance Group to the Safety & Quality Group. New consultant has been engaged to carry out management surveys at all 3 sites, providing project management and expert witness services to the Trust. | Levels of exposure experienced are unknown. Exact number of persons potentially exposed unknown. Access restrictions on some plantrooms may delay reactive maintenance activity, potentially impacting on clinical activity or patient safety. | 3 | 5 | 15 Down from 20 | The Trust is working with the HSE to address all issues arising from previous incidents based on an Action Plan developed in response to the HSE prosecution - to be reviewed first-half of October. During implementation of this Action Plan further gaps in assurance were identified, and a new Management Survey is underway to provide the baseline for revisions to both the Asbestos Management strategy and Plan. This work will be complete by 30 Nov 15. (Mitigation measures, including restricted access to some areas, are in place to ensure patients, staff and visitors are not at risk from ACMs during this period). Funding is allocated in 2015/16 to complete remedial work in plantrooms (by 31 Mar 16). HR are coordinating action relating to any employees (incl contractors) who may have been exposed to ACMs in the period under consideration by the HSE. | 3 | 2 | 6 | 2015-10-14 | SQC
3155 | PR 3 | Medicine | Gastroenterology | Kevin Howell | 2014-07-28 | Failure to deliver the planned expansion of the Endoscopy Unit Failure to deliver the endoscopy expansion plan will result in: -Endoscopy unit not achieving Level A for timeliness of waiting national targets for 3 consecutive months resulting in change to JAG status; -Loss of JAG accreditation leading to loss of reputation, ability to train endoscopists and will lead to loss of our current bowel screening programme (worth £800,000) -Bowel Scope screening unable to expand to running 10 lists by March 2018 (1 list currently running, 1 due to start in Oct 2015 and 1 more to commence in Mar 2016) -Loss of income to the Trust (Income loss calculated to be -Bowel Scope lists on full roll out is £1.8M PA and Symptomatic list income is £2.26M PA) -Inability to meet national targets for symptomatic and suspected cancer patients within national standards -Surveillance cases being pushed out beyond 3 months | 4 | 5 | 20 | Recruited 4 (1 on mat leave) and training in place for nurse endoscopists Nurse Endoscopist starting 01/09/2015 - Band 5 Bowel scope screening list running at Watford; Cystoscopy service has been moved to pre-op assessment Endoscopy expansion plan signed off by the Trust Endoscopy project plan group in place Saturday & Sunday lists running to cope with demand and meet national targets; Staff Interviews for Endoscopy nurses took place w/c 27/07/2015 - 2 recruited & working their notice due to start 1st Sept 15 and the other early Oct 2015. | Endoscopy expansion plan not implemented and no clear Project Plan Job descriptions not matched Increase in number of referrals No space to run additional lists according to plan; Not enough Nurses to cover - links into divisional risk 3062 Still short of a Band 7 | Cystoscopy move confirmed - TLEC Minutes Endoscopy expansion plan signed off Minutes from endoscopy planning group Cancer referral lists | Further work on governance requirements needed - reporting and oversight group/committee. | 4 | 4 | 16 | Endoscopy expansion plan to be implemented to enable endoscopy service to deliver the lists in line with national targets; Actionee - Risk owner, Date - March 2016 Cystoscopy has moved out; options to be discussed with Bruce McFarlane, Kevin Howell & Lynn Hill. Band 7 Recruitment to be actioned; Actionee - Emma Purkis, Consideration being given to outsourcing some surveillance work Earlier start times still being considered | 4 | 2 | 8 | 2015-10-14 | SQC
2883 | PR 3 | Environment | Estates services | Kevin Howell | 2012-01-13 | Legionella and other Bacteria Management and control of water systems Age and poor condition of the infrastructure increases the risk of vulnerable persons becoming infected by Legionella or other bacteria present in the water distribution system. | 4 | 4 | 16 | Risk Assessment undertaken in 2012. Action Plan developed and all highest rated risks mitigated by Backlog maintenance programme in 2013/14 & 2014/15 (tank replacement, deadleg removal and re-engineering of ITU hot and cold water systems). Water Safety Plan, endorsed by Trust in 2013, provided management Action Plan to mitigate all risks to acceptable level. Plan has been implemented and includes water sampling and flushing programmes, TCV maintenance and replacement of calorifiers. Results and remedial action monitored through Water Safety Group and Infection Prevention and Control dashboard. Water sampling in place across Trust including all high risk areas at frequency required in HTM. Robust system in place to mitigate risk from any non-compliance. | There are still some gaps in flushing records. Much of hot and cold water distribution system is old and in need of replacement, increasing risk that bacteria can thrive. Annual Risk Assessment, as required by Water Safety Plan, is overdue - this is an outstanding HSE requirement following HSE Notice of Contravention issued to Trust in December 2013. | Creation of Water Safety Group, reporting through Infection Prevention & Control and Safety & Quality Groups, to provide assurance that management processes are effective. Comprehensive reporting of all results, non-compliance and remedial actions available to DIPC and Chief Microbiologist on Trust intranet. Immediate implementation of contingency plan (including use of point of use filters, flushing and disinfection),when high counts are received. Independent annual audit of Trust water management system by external specialist reporting findings through Water Safety Group. Trust safe system of work complies with HTM requirement. | External audit and risk assessment overdue. Without accurate engineering drawings of water distribution systems full assurance cannot be provided. | 4 | 4 | 16 | Improve reporting of water quality info to IPC. Complete Risk Assessment by end October 2015. Carry out all High & Medium Risk remedial works identified in Risk Assemment by 31 Mar 16. Progress the Water Safety Plan in accordance with programme (ongoing annual requirement). Complete external audit and Risk Assessment by 30 Oct 15. Close out HSE Notice of Contravention by 16 Nov 15. Prioritise investment to close out all High risks identified in Risk Assessment by 31 Mar 16. | 4 | 2 | 8 | 2015-10-14 | SQC
3501 | PR 3 | Environment | Estates services | Kevin Howell | 2015-06-17 | Non-Compliance with HTM 00 - Provision of a Safe System of Work The NHS and HSE requires the Trust to demonstrate that it operates a "Safe System of Work" across its high risk estate management activities. The mandated system is based on suitably trained, skilled and experienced staff at each level within the maintenance organisation; formally appointed to specific identified roles. Demands on the workforce, reliance on Agency staff and removal of the training budget have left the Estates Team unable to meet the level of assurance required by HSE / HTM. Currently less than 50% of the mandated positions required to satisfy HTM 00 are filled by permanent staff. Although the new Estates structure provides basis for full compliance, this will not be achieved until recruitment is complete and all staff are trained and appointed. An external gap analysis identified a lack of evidence that the trust is compliant with the HTM in areas including electrical safety, the management of medical gases, steam, ventilation, pressure and gas systems, lifts, working at heights and in confined spaces. | 4 | 5 | 20 | Head of Engineering has undertaken internal risk assessment to ensure all high risk activities are managed, supervised and undertaken in a safe manner. The new Estates structure, when fully recruited, will provide appropriate management, supervision and expertise at all levels on all 3 sites. Key safety functions (HV, water management, medical gas, pressure systems, gas systems) are currently supported by appropriately skilled external contractors and/or Agency staff. | The current arrangements do not meet the requirements laid down in HTM 00, most specifically the requirement for all appointed Authorised Persons (APs) to have site specific experience. This HTM mandated model is used by the HSE to confirm that a Trust operates a Safe System of Work. | New Environment Division management structure includes provision of monthly compliance audit to Divisional Governance Group. Independent Authorising Engineers provides annual audit of high risk activities, reporting through Divisional Governance Group to Safety & Quality Group. | Divisional Governance Group and supporting compliance structure will not be in plance until 30 Nov 15. Some disciplines (pressure systems, ventilation, working at heights, confined spaces) are not currently subject to external audit. Authorised Persons have not been formally appointed to role. In event of a serious incident involving estates activity, the Trust would not be able to use the HTM mandated model to demonstrate it was operating a safe system of work. | 4 | 4 | 16 Was 15 | Recruit to all vacant posts in Estates & Compliance teams by end Dec 15. Secure training budget for 2016/17 to cover HTM 00 requirements. Expand external audit to cover all high risk activities by 31 Mar 16. Ensure all findings from AE audits are reviewed, within a month, by the Divisional Governance Group, and escalated where necessary to Quality & Safety Group (ongoing requirement). Ensure all essential Authorised Persons, Authorising Engineer and Competent Persons appointments are covered by either Trust staff, Agency or contractors by end Dec 15. Undertake quarterly internal compliance audits, reporting through the Divisional Governance structure to Safety and Quality Group (from 1 Dec 15) In year funding gap for training of Authorised Persons / Competent Persons to be covered from defering planned works to 2016/17. | 4 | 3 | 12 | 2015-10-14 | SQC
3144 | PR 3 | Environment | Estates services | Kevin Howell | 2014-07-21 | Working Environment - Occupational Health, Watford Occupational Health (OH) Department (H-Block Watford General Hospital) The area is currently assessed as unfit for clinical use due to the condition of building, the environment and the space/facilities available. Despite significant investment it has been impossible to stop widespread and invasive damp across the rooms occupied by OH. The environment has been stated as the cause of long-term sickness within the OH staff team. The current area does not meet the minimum mandated requirement for delivery of clinical services (access, infection control, privacy & dignity). | 4 | 5 | 20 | Monitor situation including condition of building fabric (internal and external) and the clinical environment as winter approaches. Identify any short-term remedial work / action that can be undertaken to alleviate mitigate current risk | Lack of suitable area to re-locate the department in the short-term. | Undertake monitoring of air quality to assess potential impact on staff. | Unable to confirm new location for OH or timescale for move. | 4 | 4 | 16 Was 15 | The only mitigation is the relocation of the service. Suitable facilities have been identified on the Watford site, but are subject to conflicting demands. The Interim Estates Strategy, currently in draft form, will confirm the best option. The capital programme may need to be prioritised to facilitate any enabling work. The Plan to relocate OH to be confirmed by 16 Nov 15, and the department will be relocated by 31 Mar 16. This risk will then close. | 4 | 2 | 8 | 2015-10-14 | SQC
2809 | PR 3 | Environment | Estates services | Kevin Howell | 2012-02-10 | Security Access System The door access system in use at WGH has exceeded its design capacity. Passes issued to new employees, including clinical staff,are not providing access to all areas; creating the possibility that members of the Crash Team may not be able to respond in the necessary timescale. NEW - Escalation Agreed at RRG Setember 2015 | 5 | 3 | 15 | All security access passes are issued by Facilities. Current system ensures that access to 'restricted' areas is only provided to essential staff. System is constantly reviewed and maintained by Facilities & external contractor. | Current system has exceeded capacity, resulting in new pass holders being unable to access assigned areas. Current system cannot be expanded without circa £60k (currently unfunded) capital expenditure. | Current system provides high level of assurance that access to clinical areas is restricted to appropriately assessed personnel only. | Inability to provide assurance that passes issued to personnel arriving in the Trust after 1 Sep 15 creates the possibility that personnel responding to a crash call may not reach the patient in the time necessary to 'treat' the medical emergency. | 5 | 3 | 15 Was 9 | Initiate immediate action to re-designate sufficient cards to guarantee unrestricted card access to all members of the crash team, if necessary by removing lower priority personnel from the system by 18 Sep 15. Initiate capital project to replace current system with robust and future-proofed card access system at WGH by 30 Oct 15. | 5 | 1 | 5 | 2015-10-14 | SQC
2145 | Pr 4 | Clinical Informatics | Data Quality | Lisa Emery | 2009-02-13 | Loss of the Hemel or Watford Data Centres Risk: Data Centres damaged or links to data centres severed. Cause: Physical data centre housing is not fit for purpose therefore risk of damage through fire, water, temperature, humidity, sabotage (physical, virtual), power. Consequences: Prolonged and material loss of IT services hosted from the data centres will seriously hinder WHHT's ability to support the delivery of safe patient care. These services include key clinical and operational IT systems. | 4 | 4 | 16 | 1. Physical security controls in place to restrict access to authorised personal only; 2. Fire suppression systems installed; 3. Mains power supply fed from the site generator and room UPS mitigates interruptions in power during cutover to generator; 4. Some key IT systems are replicated in both data centres; 5. Temperature controls monitored for increases above normal; 6.Make IT Happen application migration will reduce the dependency on the Trust Data Centres | There is only a limited contingency plan in respect of catastrophic system loss. The current situation at the Hemel Data Centre is deteriorating with the roof leak increasing in size and evidence of water in the light fittings and on the airconditioning units | Internal audit reports/NIMS review. Make IT Happen applications migration plan rollout prioritised through Informatics Group. Progress monitored via Informatics Group and F&P Committee | Infrastructure Review/Disaster recovery Plan drafted not yet implemented. | 4 | 4 | 16 | Estates are aware and have instructed contractors to investigate the roof at Hemel. Full repairs are currently underway. Make IT Happen applications migration due to complete January 2016. | 4 | 1 | 4 | 2015-10-14 | SQC
3448 | PR 4 | Clinical Support | Radiology | Lisa Emery | 2015-04-13 | PACS Data Storage Cause: The Trust is required to localise the PACS images currently stored at the Accenture Data centre by June 2016. HSCIC has put in place a national process / slot plan to allow for data to be migrated to locally hosted solutions. WHHT ‘slot’ was allocated for August 2015. The plan had been to transfer the data to the Trust’s Outsourced IT partner however they have not been able to provide an appropriate solution within the agreed timeframe. HSCIC require trust to confirm its plan for data migration by 23.09.15 and for transfer to be effected by 1st November 2015. Effect: If the Trust is not able to conform to this requirement there is a risk that migration is not able to be completed within the national timescale resulting in potential for significant loss of patient level clinical data. Impact: Loss of this data will result in potential delays in diagnosis for some patients by preventing review of past imaging, preventing comparison of current and past imaging. This will affect patient care and safety and also presents a medico-legal and financial risk to the Trust. NEW - Escalation Agreed at RRG Setember 2015 | 4 | 3 | 12 | Project manager assigned to this project and urgently investigating alternative local storage solutions in context of failure of original plan. Weekly project team meeting in place. AD, ICT providing senior oversight and support to solution finding. | No firm plan or funding agreed as at 17/09/15. | Escalated to Chief Information Officer and Divisional Director, Clinical support services. Imaging Informatics group provides oversight of project, reporting to Informatics Group. F&P sub committee provides assurance to Board re IM&T risks. | None Identified | 4 | 4 | 16 Was 9 | Urgent review of options, feasibility and costs. Plan to be provided to Accenture by 23.09.15. Update to be provided to F&P on 22.09.15. Funding and procurement solution to be identified and approved (with appropriate waivers if required) by 23.09.15. Identified solution needs to be implemented by 1st November 2015 to ensure data migration slot not missed and minimise risk of data loss. | 4 | 2 | 8 | 2015-10-14 | F&PC
3120 | PR 4 | Medicine | Outpatient Nursing Services | Lynn Hill | 2014-07-09 | Patient Medical Notes missing, Delayed or poor condition. There are a number of issues with the storage, transportation and management of health records in the Trust, which are cumulatively resulting in notes not always being delivered in a timely manner or being available for appointments. The issues are detailed below: a) Space - the Trust has 2 Health Records Libraries, one at WGH and one at HHGH. Due to limited storage space only the records of patients who have attended within the past year are kept on site, with the remainder having to be stored off-site within the secure archive. There is also a significant space issue in Clinic Prep at WGH, as the working environment is overcrowded with insufficent storage, which results in inefficiencies. b) Logistics - notes have to be transported between the 3 sites, which is inefficient and coupled with the existing space issues, often means that the notes for the most acute patients who attend WGH cannot always be stored at WGH Library due to their size (HHGH's Library is larger). c) IG - compliance with the tracking process is poor across the Trust, leading to notes being reported as 'lost' and then being found after intensive searches by the Health Records team. d) Resource - Outpatient activity (which directly impacts the Clinic Prep team) has increased 24% over the past 5 years, with limited review of the Clinic Prep staffing establishment, meaning that the team are having to utlise a high number of bank and agency staff to maintain service which results in instability and decreased efficiency. e) Technology - the Trust does not currently have a strategy for Electronic Patient Records, therefore is not currently harnessing technology that could resolve some of these inefficiencies and therefore improve the patient and clinician experience. | 4 | 5 | 20 | Patient are verbally informed if the notes are missing Nurse staff contact medical records to find required patient records Access to Infloflex to attain limited patient information; | All information not available on infoflex | Incident forms Appointment cancellation due to lack of notes Complaints for cancellation of appointments | Possible breaches in RTT | 4 | 5 | 20 | a) Space - Director of Estates is now working with the Health Records team to identify possible solutions, acknowledging the interdependencies with the Electronic Health Record strategy (see below) and the MRI scanner which will be installed in the WGH Clinic Prep work space by March 2016; b) Logistics / Resource / Technology: The Trust is now working on an Electronic Health Records strategy which will set out the plan for the next 2-5 years and will include proposals to reduce staffing costs and improve efficiency by implementing an effective IT solution. Options include barcoding of records; location-based tracking; scanning of health records; outsourcing of library/prep function; c) Consideration of options to improve medical records tracking, eg tracking by location rather than terminal digits. This is expected to deliver reduced reliance upon additional bank staff, with the potential to release other medical records staff who could be reallocated to clinic preparation duties; d) Clinical Informatics working with Medical Records Department to improve tracking process; e) Business case for move, Sept 15 | 4 | 2 | 8 | 2015-10-14 | F&PC
3483 | PR 5 | Medicine | Care of the Elderly | Lynn Hill | 2015-06-11 | Patient Flow, delayed transfers and medical outliers (medicine) Due to the high number of DTOC patients in the hospital, beds are blocked, causing bottlenecks at the front door and queues in A&E leading to long trolley waits, patients not placed on the best ward for their care etc, and the DTOC patients themselves may deteriorate in hospital waiting for onward services. There appears to be a significant lack of capacity in external organisations to be able to manage the flow of patients out of hospital causing the whole process to become slow and congested. | 4 | 5 | 20 | "Automated referral process being trialled to speed up the pathway. Integrated discharge service currently under review to improve the way patients are supported out of hospital Tudor and castle wards are dedicated for patients awaiting care packages Regular SRG meetings to manage the position at Executive level Weekly patient specific review meetings held by the Integrated Discharge Team Weekly operational meeting established between WHHT, HCT and HCC to identify blockages which can be resolved locally " | "Ability to enhance the availability of resources from social care Tudor / Castle wards receiving patients who do not meet cirteria or whose medical condition deteriorates post admission " | System Resilience Group and HCC commitment to reduction - weekly / monthly trend data Incidents Complaints Week on week reduction in DTOCs | DTOC levels remain high | 4 | 4 | 16 | "Robust winter planning for 15/16 to ensure that appropriate surge capacity is available; Review of Configuration of beds to be undertaken and a paper to go to CAG; Need to engage medical & nursing leadership in implementation of standards on all wards as part of the 'perfect ward' roll out plan;" | 4 | 2 | 8 | 2015-10-14 | F&PC
3577 | PR 7 | Finance |  | Don Richards | 2015-07-29 | Failure to develop and implement sufficient efficiency initiatives to support financial plan Cause: Failure to develop and implement sufficient efficiency initiatives to support financial plan. Effect: Less income and/or more expenditure than planned. Impact: - Failure to meet financial plan targets (£29.2m deficit) Difficulties in making cash available to pay suppliers and staff Reputational damage arising from failing to meet targets. Damaged credibility for long term Trust strategy. | 4 | 4 | 16 | - Structured efficiency programme - Specialist advisory support. - Project plans produced with timescales interdependencies etc. - Performance management system - Quality impact assessment signed off by CMO and Chief Nurse. | Agreed consequences for inadequate performance | Performance reports to Divisional Performance reviews. CFO report to Finance Committee and Board. Reports provided by external advisory firm. TDA performance reviews Internal Audit reports. External Audit reports. | Assurance that poor performance in contributing to the efficiency programme is managed | 4 | 4 | 16 | Ensure that performance in contributing to the efficiency programme is included in staff appraisals (April 2016) | 4 | 2 | 8 | 2015-10-14 | F&PC
3414 | PR 7 | Finance |  | Don Richards | 2015-04-08 | Loss of income resulting from the Trust failing to achieve requirements set out in the CQUIN schedule Loss of income resulting from the Trust failing to achieve requirements set out in the CQUIN schedule | 5 | 4 | 20 | Monthly review of progress against individual CQUINs to identify income effects of any non-compliance. Financial risks for CQUIN revised accordingly and non-compliance escalated to the Executive Team. | Divisional ownership of CQUIN target | Information processed regularly by team that is able to interpret and explain the implications to Divisions and Executive team | Potential delay in CCG feedback on our CQUIN delivery | 5 | 3 | 15 | Ongoing discussions with commissioners highlighting areas of concern. Action plans produced to achieve targets. | 5 | 2 | 10 | 2015-10-14 | F&PC
3420 | PR 7 | Finance |  | Don Richards | 2015-04-08 | There is a risk that the CCG could use the contract levers to penalise the Trust The CCG would be using the contract levers to penalise the Trust for non-performance against nationally and locally mandated targets. This will lead to a loss of income which would worsen the Trust's financial position. This loss will need to be offset by non-recurrent support from the CCG. This non-recurrent support is yet to be agreed. | 5 | 3 | 15 | Ongoing discussions with the CCG to seek clarification regarding re-investment. Trust position made clear to TDA in monthly IDMs | There remains a disconnect between CCG investment of penalties and Trust expectations | Kept on the agenda of QCR meetings and on meetings between CFOs | Disconnect between CCG & Trust priorities | 5 | 3 | 15 | Continue to report our position and escalate to TDA. Ongoing discussions with the CCG to seek clarification regarding re-investment. Kept on the agenda of QCR meetings and on meetings between CFOs Trust position made clear to TDA in monthly IDMs | 5 | 1 | 5 | 2015-10-14 | F&PC